## Jira
Summary | Issue Type | Status | Resolution | Assignee | Creator | Resolved | Due date | Assigned to | Custom field (Completed Date) | Sprint | Custom field (Start Date)
configure AWS RDS MySQL to connect with backend python utilities | Task | To Do |  |  | Hrushikesh Joshi |  | 2024-04-10 | Aashlesha Shirole, Sreeja Reddy Karukonda,Sujay Sail |  | SCRUM Sprint 3 | 2024-03-14
configure EC2 instance to execute working environments for the app | Task | To Do |  |  | Hrushikesh Joshi |  | 2024-04-10 | Aashlesha Shirole, Sreeja Reddy Karukonda,Sujay Sail |  | SCRUM Sprint 3 | 2024-03-14
design and create database tables | Task | In Progress |  |  | Hrushikesh Joshi |  | 2024-03-13 | Ashish Sudam |  | SCRUM Sprint 2 | 2024-02-15
create AWS EC2 instance to run backend utilities | Task | Done | Done |  | Hrushikesh Joshi | 2024-03-12 23:08 | 2024-03-13 | Sujay Sail | 2024-03-06 | SCRUM Sprint 2 | 2024-02-15
create resume upload page where users can upload their resumes | Task | Done | Done |  | Hrushikesh Joshi | 2024-03-12 23:06 | 2024-03-13 | seung, Yash Jani | 2024-02-29 | SCRUM Sprint 2 | 2024-02-15
create AWS RDS DB instance and connect to local MySQL Server | Task | Done | Done |  | Hrushikesh Joshi | 2024-03-12 23:05 | 2024-03-13 | Sreeja Reddy Karukonda | 2024-02-17 | SCRUM Sprint 2 | 2024-02-15
create backend api interaction utility to collect data from job board api | Task | Done | Done |  | Hrushikesh Joshi | 2024-03-12 23:05 | 2024-03-13 | Hrushikesh Joshi | 2024-02-28 | SCRUM Sprint 2 | 2024-02-15
create backend utilities to extract critical information from a resume. | Task | Done | Done |  | Hrushikesh Joshi | 2024-03-12 23:05 | 2024-03-13 | Hrushikesh Joshi | 2024-02-24 | SCRUM Sprint 2 | 2024-02-15
create dashboard to view all available jobs along with some use tracking data | Task | Done | Done | seung | seung | 2024-03-12 20:06 | 2024-03-13 | Yash Jani | 2024-03-08 | SCRUM Sprint 2 | 2024-02-15
Deliverable#2 Retrospectives | Task | Done | Done | seung | seung | 2024-03-13 00:11 | 2024-03-13 | Aashlesha Shirole, Ashish Sudam, Hrushikesh Joshi, Seung, Sreeja Reddy Karukonda, Sujay Sail , Yadu Vamsikrishna Yadav Udatha, Yash Jani | 2024-03-12 | SCRUM Sprint 2 | 2024-02-15
Deliverable#1 recording | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Deliverable 1 Retrospectives | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Identify team roles and responsibilities | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Set up GitHub Wiki page | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Get Approval | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Discussion of the project ideas | Task | Done | Done |  | seung | 2024-03-12 19:50 |  |  |  | SCRUM Sprint 1
Deliverable#1 PPT | Task | Done | Done |  | seung | 2024-03-12 19:46 |  |  |  | SCRUM Sprint 1
Deliverable#2 PPT | Task | Done | Done | seung | seung | 2024-03-13 00:11 | 2024-03-13 | Aashlesha Shirole, Ashish Sudam, Hrushikesh Joshi, Seung, Sreeja Reddy Karukonda, Sujay Sail , Yadu Vamsikrishna Yadav Udatha, Yash Jani | 2024-03-12 | SCRUM Sprint 2 | 2024-02-14
create flexibility in resume input(docx ,pdf ,txt) | Story | To Do |  | Yadu Vamsikrishna Yadav Udatha | Yadu Vamsikrishna Yadav Udatha |  | 2024-04-10 |  |  | SCRUM Sprint 3 | 2024-03-12
create a filter to search user-defined keywords( location, salary range, company size, or job type) | Story | To Do |  | Yadu Vamsikrishna Yadav Udatha | Yadu Vamsikrishna Yadav Udatha |  | 2024-03-13 |  |  |  | 2024-02-15
should implement job ranks based on keyword matching between resume and job descriptions | Story | To Do |  |  | Ashish Sudam |  | 2024-04-24 |  |  | SCRUM Sprint 3 | 2024-03-12
expand job search to include other job boards beyond Reed.co.uk | Task | To Do |  |  | Ashish Sudam
Integrate the app with a file system server | Story | To Do |  | Yash Jani | Hrushikesh Joshi |  | 2024-04-10 |  |  |  | 2024-03-14
create login page for the users to navigate through their account | Task | In Progress |  | seung | Hrushikesh Joshi |  | 2024-04-10 | seung, Yash Jani |  | SCRUM Sprint 3 | 2024-03-14
create sign up page where users can register on the SmartHirePro app | Task | In Progress |  | seung | Hrushikesh Joshi |  | 2024-04-10 | seung, Yash Jani |  | SCRUM Sprint 3 | 2024-03-14
create a config file to store configuration of the backend | Story | To Do |  | Hrushikesh Joshi | Hrushikesh Joshi |  | 2024-04-10 |  |  | SCRUM Sprint 3 | 2024-03-15
create backend utility to parse job data from the job board api | Task | In Progress |  | Hrushikesh Joshi | Hrushikesh Joshi |  | 2024-04-10 | Hrushikesh Joshi |  | SCRUM Sprint 3 | 2024-03-15
create a model to compare similarity of a job description and user skills | Task | To Do |  | Hrushikesh Joshi | Hrushikesh Joshi |  | 2024-04-10 | Hrushikesh Joshi |  | SCRUM Sprint 3 | 2024-03-14
create backend utilities to upload user information to a database | Story | To Do |  | Hrushikesh Joshi | Hrushikesh Joshi |  | 2024-04-10 |  |  | SCRUM Sprint 3 | 2024-03-14